INVESTMENT COMMITTEE MEMORANDUM

Project Helios Solar & Storage

Acquisition of an 80% controlling stake | Thailand | June 2026

IMPORTANT: This document and all figures are entirely synthetic and were created solely for a proof-of-concept demonstration.

# 1. Decision requested

Approval is requested to proceed to final documentation and financing for the acquisition of an 80% controlling interest in Project Helios, subject to the conditions precedent and open items set out in this memorandum.

| Item | Detail |
| --- | --- |
| Requested approval | Commit up to USD 81.8 million of sponsor equity, including transaction costs and contingency. |
| Asset | 250 MWac / 320 MWp solar PV plus 100 MW / 200 MWh BESS. |
| Location | Nakhon Ratchasima, Thailand. |
| Stage | Late-stage development; construction targeted to commence in Q1 2027. |
| Proposed ownership | 80% Group / 20% local development partner. |
| Target COD | 30 September 2028. |

# 2. Executive summary and investment rationale

Establishes a scalable solar-plus-storage platform in a priority Southeast Asian market.

Combines a 20-year contracted revenue base for 70% of generation with merchant and grid-services upside.

Provides control rights and a pipeline option over two adjacent development sites.

Base-case equity IRR is stated at 14.2% in this memorandum, above the illustrative 12.5% hurdle rate.

Key challenges are grid reinforcement cost, merchant-curve support, BESS augmentation, land easements and offtaker credit evidence.

# 3. Strategic fit

Project Helios supports the stated growth priorities of expanding utility-scale renewables, adding flexible capacity and building a presence in Southeast Asia. The transaction also increases exposure to Thailand and to one synthetic public-sector offtaker. The submission does not quantify the resulting portfolio concentration by geography or counterparty.

# 4. Transaction overview and structure

| Item | Detail |
| --- | --- |
| Seller | Meridian Renewables Thailand Co., Ltd. (synthetic). |
| Transaction | Acquisition of 80% of the project company at financial close. |
| Enterprise value | USD 276 million illustrative enterprise value. |
| Project cost | USD 292 million stated in this memorandum. |
| Governance | Three of five board seats, CEO nomination right, and reserved-matter vetoes. |
| Development partner | Retains 20% and provides local development services through COD. |

# 5. Technical description and development status

| Item | Detail |
| --- | --- |
| Solar facility | 250 MWac / 320 MWp fixed-tilt bifacial PV. |
| BESS | 100 MW / 200 MWh lithium iron phosphate system. |
| Expected net generation | Approximately 545 GWh in the first full operating year. |
| Net capacity factor | 24.9%. |
| Availability | 98.5%. |
| Curtailment assumption | 2.5% base case. |
| EPC strategy | Single-wrap fixed-price EPC contract under negotiation. |
| Permitting | Core generation licence obtained; final grid easements and two local construction permits remain open. |

# 6. Market, offtake and revenue model

Seventy percent of solar output is assumed to be sold under a 20-year synthetic PPA at USD 58/MWh in 2029 with 1.5% annual escalation. The remaining 30% is exposed to a synthetic merchant curve starting at USD 65/MWh. BESS revenue is assumed to arise from capacity availability, energy shifting and ancillary services. The independent merchant-price study is referenced but not included in the submission pack.

PPA counterparty: Provincial Electricity Partnership (synthetic).

Payment security: three-month letter of credit is under discussion but not executed.

No independent credit rating or payment-history analysis is appended.

Merchant upside is a material contributor to equity returns.

# 7. Financial case

| Metric | Management case | Unit | Comment |
| --- | --- | --- | --- |
| Total project cost | 292.0 | USD mn | Differs from deck and workbook |
| Project IRR | 10.3 | % | Nominal post-tax |
| Equity IRR | 14.2 | % | Memo value |
| NPV | 39.0 | USD mn | At 9.0% discount rate |
| Minimum DSCR | 1.32 | x | Base case |
| EV / EBITDA | 9.3 | x | First full-year EBITDA |
| Debt / total cost | 65.0 | % | Senior project financing |
| Year-one revenue | 38.6 | USD mn | First full operating year |

# 8. Valuation and benchmark context

The proposed enterprise value implies approximately USD 1.10 million per MW of solar capacity and 9.3x first full-year EBITDA. Management states that these metrics are broadly consistent with recent renewable transactions, although the comparable-company and transaction set, normalization adjustments and source dates have not been appended.

# 9. Financing and execution plan

65% senior debt at an illustrative 6.4% all-in interest rate and 15-year post-COD tenor.

Remaining project funding from sponsor equity in proportion to ownership.

Financial close targeted for December 2026 and construction start for March 2027.

Grid-connection reinforcement estimate remains subject to utility confirmation.

Hedging policy is described, but executed FX and interest-rate hedge terms are not included.

# 10. Sensitivity analysis

| Scenario | Equity IRR | Minimum DSCR |
| --- | --- | --- |
| Base case | 14.2% | 1.32x |
| Merchant price -15% | 12.2% | 1.24x |
| Generation -5% | 12.6% | 1.21x |
| Capex +10% | 11.8% | 1.30x |
| COD delay 6 months | 11.9% | 1.28x |

The pack does not include a combined downside case or a BESS degradation/augmentation sensitivity.

# 11. Key risks and mitigants

| Risk | Assessment | Mitigation / status |
| --- | --- | --- |
| Merchant price exposure | Medium-high | 70% contracted; downside sensitivity included but independent curve absent. |
| Grid cost and schedule | High | Utility design review ongoing; estimate includes USD 25m. |
| Construction and supply chain | Medium | Fixed-price EPC planned; liquidated damages under negotiation. |
| BESS degradation | Medium-high | Warranty term sheet available; augmentation budget not separately modelled. |
| Offtaker credit | Medium | Payment-security package under negotiation; independent credit review absent. |
| Land and permits | Medium | Most parcels secured; final easements and two permits remain open. |
| Cybersecurity | Not assessed | No dedicated EMS/SCADA cyber assessment included. |
| Decommissioning | Not assessed | No funded decommissioning or battery-disposal reserve included. |

# 12. Governance and shareholder arrangements

The Group will appoint three of five directors and nominate the chief executive. Reserved matters cover budget, financing, material contracts, asset disposal, related-party transactions and changes to the business plan. The minority partner retains customary information and pre-emption rights.

# 13. ESG, legal and regulatory

The project is assumed to have completed a preliminary environmental and social assessment. Key open items are closure of community-access commitments, final biodiversity monitoring protocol, two land easements and construction-permit updates. No material litigation has been identified in the synthetic diligence summary.

# 14. Recommendation and conditions

Approve progression to final documentation, subject to reconciliation of financial metrics across all submission documents.

Require independent merchant-price and offtaker-credit evidence before final commitment.

Require a combined downside and explicit BESS augmentation sensitivity.

Cap grid and advisory costs and reconcile potential overlapping technical and legal scopes.

Require closure of land, permitting, cybersecurity and decommissioning-funding actions.

# Appendix A - Submission data-room references

ADB_Gulf_Solar_BESS_Project_Page.pdf - public comparator reference.

ADB_Gulf_Solar_BESS_IEE.pdf - public environmental comparator reference.

IFC_Candi_Solar_CI_SII.txt - public solar/BESS investment disclosure comparator.

IFC_FRV_Solar_India_SII.txt - public solar investment disclosure comparator.

2024_v3_Model_Parameters.csv - public technology benchmark data.

WorldBank_PPI_Energy_Renewables_2000_2024.xlsx - public infrastructure project comparator data.